## Slide 1
BELL ACQUA LAKE
90-Day Growth Roadmap
Turning the client Growth Strategy into a week-by-week execution plan
August – October 2026 · $1,000/mo working ad spend, engineered for ROI
Prepared by Anti-Gravity · Companion to: Marketing & Revenue Performance Analysis · July 2026

## Slide 2
The Goal, and Why It Is Winnable
THE ONE-LINE THESIS
This is a lead-generation problem — not a capacity or conversion problem.
The boats, coaches, and 10 daily slots already exist and sit mostly idle. Hitting the numbers is about putting more qualified leads into a funnel that already converts — so every marketing dollar compounds into lessons, then memberships.
$25K
Gross revenue / month
Sustained Aug · Sep · Oct
15
New ski memberships
By Oct 31, 2026
$15K
Cash reserve
Banked to carry winter
$1K
Working ad spend / mo
≈ 8× the recent average
These targets are one lever, not four: 15 members at the client’s ~$4,000 season value ≈ $60,000 — the membership push drives revenue and reserve at the same time.

## Slide 3
The Numbers Behind the Target
CAPACITY IS NOT THE CONSTRAINT
10 slots / day open
Coaches, drivers and boats are already staffed to run all 10. The single busiest day this season used just 8.
~90 idle days ahead
Across the Aug–Oct window, most lesson capacity sits unused. The bottleneck is lead volume — leads need to roughly triple.
A genuine new high
September has cleared $25K in 2 of the last 4 years. Doing it all three months is a record — reachable, but only on real lead volume.
Monthly revenue: 4-year average vs. $25K target
Chart: 
| August | September | October
4-Year Avg | 19525 | 22898 | 20179
$25K Target | 25000 | 25000 | 25000
History is trending down (2025 was the weakest year) — so the plan cannot rely on “better conversion on today’s traffic.” It needs more leads.

## Slide 4
The Growth Funnel We Are Feeding
THE PROVEN PATH — EVERY STAGE ALREADY WORKS
LEAD FB/IG lead form, DM or call
$1.81–$3 per lead
LESSON BOOKING First Beg/Int lesson or ski ride
~62% margin · 10 slots/day
REPEAT CLIENT Comes back for more lessons
~$1,000 avg spend
MEMBER The prize — near-pure margin
~$4,000 / season
27.5%
of paying members came from a lesson
11 of 40 memberships, worth $28,222 in current contract value — dollar-backed proof the pathway works.
Working backward: ~150 lesson bookings this quarter (≈12/week) delivers 15 members at a conservative 1-in-10 rate — well within capacity. The job is filling the top of the funnel.

## Slide 5
Why Every Marketing Dollar Compounds
THE ROI ENGINE — MARGIN BY PRODUCT LINE
~62%
Lesson & ski-ride margin
After paying instructors, drivers and fuel. Every extra booking is genuinely profitable — not a break-even lead-gen loss.
~100%
Membership & rental margin
Membership, lake rental and boat storage carry no direct cost in the P&L — near-pure margin against fixed overhead.
$400/hr
Private-event boat hire
Boat cost is already sunk. A 3-hr charter grosses $1,200 at very high margin — no instructor needed, only driver + fuel.
The compounding effect. The lesson that pays for itself at ~62% margin is also the doorway to a membership sale that carries close to 100% incremental margin. That is why the plan pours budget into the top of the funnel: the first sale funds the acquisition, and the second sale is almost all profit.

## Slide 6
The $1,000 / Month Budget
8× THE RECENT WORKING AD SPEND — PROTECTED AND DEPLOYED
Chart: 
| Paid social (Meta) — Lead objective | Testing (new audiences + creative) | Giveaway / urgency offers
Allocation | 700 | 200 | 100
$1,000
per month
$700
Paid social — Meta, Lead objective
Scale the winning Soccer-interest / affluent / frequent-traveler audience (~$1.81 CPL). Kill the duplicated “– Copy” sets. Static image creative first.
$200
Testing budget
New audiences (boating/lake-life interest, lookalike from the member list) and new creative (aerial exclusivity angle).
$100
Giveaway / urgency offers
Fund the “X spots left” urgency mechanics on the giveaway format that already works.
⚠ Guardrail: ring-fence this as working ad spend. In H1 2026 real ad spend averaged ~$128/mo (with $0 in three months) while the budget was absorbed by agency fees, design and software. Protect it, or the plan stalls.

## Slide 7
How to Read This Roadmap
THE 90-DAY ARC — THREE PHASES
AUGUST
LAUNCH & BUILD
Turn the ad engine on, stand up the follow-up sequence, secure renewals, design the private-event package.
SEPTEMBER
SCALE & TEST
Push leads toward 3×, open partnerships and the private-event line, and start measuring real conversion rates.
OCTOBER
CONVERT & CLOSE
Convert the quarter’s lesson clients into the 15 members, bank the $15K reserve, document the playbook.
OWNER TAGS — WHO IS IN CHARGE OF EACH TASK
MKT
Marketing
Anti-Gravity: paid social, organic, creative, campaigns, copy, tracking
OPS
Operations
Lake staff: scheduling, booking portal, lesson & event delivery
FIN
Finance
Owner / books: budget, collections, renewal invoicing, reserve
OWN
Owner
Client decisions: approvals, relationships, partnership & referral asks
Weekly cadence: Mon — review CPL & spend · Midweek — optimize creative/audiences · Fri — KPI snapshot & budget reallocation.

## Slide 8
August — Sprint Board
LAUNCH & BUILD
WEEK | KEY MOVES (owner in charge) | MILESTONE / KPI
Week 1 Aug 1–7 | MKT Rebuild Meta campaign: consolidate to the winning Soccer/affluent audience, kill the “– Copy” sets, launch Lead objective. MKT Ship static exclusivity creative (aerial “private lake”) + one testimonial ad. OWN Approve & ring-fence the $1,000/mo working ad budget. | Ad engine live; budget protected.
Week 2 Aug 8–14 | MKT Monitor CPL daily; pause any set > $4 CPL, scale the winner toward 3× lead pace. FIN Renewal reminders: Bettencourt ($2,000) & UC Davis Fall ($4,250), both due 8/15. MKT Turn on the automated post-lesson membership follow-up (email + SMS). | First 8/15 renewals secured; leads flowing.
Week 3 Aug 15–21 | MKT Launch fixed weekly organic cadence on @bellacqualake1 (exclusivity + real proof), 3 posts/wk. OWN Retire / merge the duplicate Bell Acqua 2 & 3 accounts into the main handle. OPS Design & price the private-event package ($400/hr → $1,200/3hr); confirm driver + fuel cost. | Organic cadence live; event package priced.
Week 4 Aug 22–31 | MKT Launch first test audience ($200): boating/lake-life + member lookalike; new aerial creative. MKT Ship referral offer: $50–100 credit to members & recent lesson clients. FIN Reconcile August: ad spend vs leads, revenue vs $25K, reserve contribution. | Baseline CPL set; referral live; Aug reviewed.

## Slide 9
September — Sprint Board
SCALE & TEST
WEEK | KEY MOVES (owner in charge) | MILESTONE / KPI
Week 5 Sep 1–7 | MKT Reallocate to the lowest-CPL audience/creative; push lead volume toward 3× baseline. OPS Publicly launch the private-event package (booking page + inquiry form). FIN Renewal reminder: Savko ($3,250) due 9/1. | Private-event line live & marketed.
Week 6 Sep 8–14 | OWN Pitch 2–3 group/institutional prospects (college ski teams, youth clubs, corporate) — the UC Davis model. MKT Build the one-page group/seasonal sell sheet for those pitches. FIN Renewal reminders: Wolfe ($2,500, 9/8), Nolden ($2,000, 9/10). | 2–3 partnership conversations opened.
Week 7 Sep 15–21 | MKT Add lead-to-customer matching (“How did you hear about us?” + Meta lead list) to capture real conversion rates. MKT A/B the post-lesson membership pitch (offer vs. social proof). OPS Drive lesson bookings toward the ~12/week pace the 15-member goal needs. | Real funnel conversion rates now measured.
Week 8 Sep 22–30 | MKT September read: leads vs 3× target, CPL trend, cost-per-booking → set October budget split. OWN Follow up partnership pitches; aim to close ≥ 1 group package. FIN Renewal reminder: Genetti ($2,400, 9/26); reconcile Sep revenue vs $25K + reserve. | Lead target assessed; ≥1 partnership advancing.

## Slide 10
October — Sprint Board
CONVERT & CLOSE
WEEK | KEY MOVES (owner in charge) | MILESTONE / KPI
Week 9 Oct 1–7 | MKT Launch membership-conversion push to ALL Aug–Sep lesson clients (email + SMS + warm call list). FIN Renewal reminder: Afrahi ($3,600) due 10/1. | Conversion campaign live to full lesson base.
Week 10 Oct 8–14 | OWN Personal outreach to highest-intent repeat clients (the proven $1K → $4K path). MKT Retarget non-converters with testimonial + member-value creative. FIN Renewal reminder: Leach ($2,400) due 10/8. | New members closed tracked vs the 15 goal.
Week 11 Oct 15–21 | MKT Keep paid social on the winning audience; protect CPL; hold organic cadence. OPS Fill remaining lesson capacity; sell off-peak private-event blocks that don’t compete. FIN Mid-October reserve check vs the $15K target. | Reserve gap quantified; capacity up.
Week 12 Oct 22–28 | MKT Last-call membership offer before winter; personal follow-ups on every open prospect. FIN Finalize collections; confirm which memberships land as cash by 10/31 vs installment. | Member count near / at 15.
Week 13 Oct 29–31 | FIN Lock the $15,000 reserve from net proceeds; final revenue reconciliation. MKT Q4 wrap report: CPL, leads, bookings, conversion rates, members, ROI on the $3K spend → scalable 2027 playbook. | 15 members · $15K reserve · documented playbook.

## Slide 11
The KPI Scoreboard
WHAT WE MEASURE EVERY WEEK — LEADING AND LAGGING
LEADING
Cost per lead
≤ $3 (best set ~$1.81)
LEADING
Leads / month
~3× baseline
LEADING
Lesson bookings / week
~12 (150 / quarter)
LAGGING
New members
15 by Oct 31
LAGGING
Revenue / month
$25,000
LAGGING
Cash reserve
$15,000 by Oct 31
Renewal safety net: ~$22,400 of existing memberships fall due inside this window. Securing them is a lower-effort path to the reserve than 15 cold members — the FIN reminder track runs all quarter.

## Slide 12
Risks, Dependencies & Data to Close
WHAT WOULD SHARPEN THE PLAN — AND WHAT COULD STALL IT
Budget leakage (top risk)
If the $1K is reabsorbed into overhead like H1, the plan stalls. Ring-fence it as working ad spend.
OWN · FIN
Lead-to-customer matching
Until a “how did you hear” field + Meta lead list exist (Week 7), true conversion rates stay assumptions.
MKT · OPS
Historical lesson-client count
Needed to convert the roster’s 27.5% into a true lesson→membership rate and forecast precisely.
FIN · OPS
Payment split: cash vs installment
Affects how much of the 15-member goal shows up as cash by Oct 31 vs later — pin down for the reserve.
FIN
Private-event capacity & cost
Confirm off-peak slots that won’t cannibalize lessons, plus real driver/fuel cost to lock margin.
OPS
Demand is the constraint
Not capacity, not conversion. The whole plan lives or dies on lead volume — so budget protection is everything.
ALL

## Slide 13
DO THIS WEEK
Five moves that start the engine
1
OWN · FIN
Approve and ring-fence the $1,000/mo ad budget as working spend.
2
MKT
Rebuild the Meta campaign — consolidate to the winner, kill the “– Copy” sets — and go live.
3
FIN
Build the renewal-reminder calendar, starting with the 8/15 due dates (~$22,400 in-window).
4
MKT
Load the automated post-lesson membership follow-up (email + SMS) into GoHighLevel.
5
OPS
Add the “How did you hear about us?” field so we start capturing real funnel data now.
The strategy is proven and the capacity is paid for. From here it is execution — lead volume in, memberships out.